DentaScale

Kickoff Checklist (internal)

Internal checklist. Target: campaigns live within 7 days of the signed agreement. Note there is no invoice at signing — the first invoice goes out at lead 30.

# Day 0 — agreement signed

- Countersign and send a copy back to the client

- Send the access guide and the onboarding questionnaire

- Add the practice to the Notion tracker and set status to Onboarding

- Book the kickoff call and send the shot list and scripts

- Confirm the client understands the $50/day ad spend commitment

# Days 1–2 — access and intake

- Confirm Business Manager access received

- Confirm Instagram is a Business account and linked to the Page

- Install the Meta pixel and verify it fires

- Confirm Google Business Profile access, if applicable

- Review the completed questionnaire and note gaps for the kickoff call

- Get calendar access, and test the lead notification and our call workflow

# Days 2–3 — kickoff call

- Agree the offer to run

- Confirm the daily budget is set to at least $50

- Agree call hours, consult slots, booking rules, and who we book (treatments, area)

- Confirm who is on camera and the date the footage is due

# Days 3–4 — footage and editing

- Receive the client's footage against the shot list (chase if late)

- Collect before-and-after images with written patient consent

- Edit into first-round ad creative

# Days 4–6 — funnel build

- Build the landing page and lead capture form

- Add the practice's reviews and social proof

- Test the full path: ad click, lead notification, our call, a test booking in their calendar

# Days 6–7 — launch

- Write ad copy and build the campaign structure

- Client approves creative and copy

- Launch, and confirm delivery within 24 hours

- Set status to Active and diarise the first weekly report

# Tracking to lead 30

- Log lead count weekly against the 30-lead invoice trigger

- Flag immediately if daily spend drops below $50

- At lead 30: send the first invoice and start the monthly billing cycle

- If day 60 approaches without 30 leads, review with the client before it lapses

DentaScale  ·  310-694-7875  ·  keyhan@dentascale.net  ·  dentascale.net